Hayah

حياة — Blood Donation App

Graduation Project  ·  Rowad Masr El Raqamiya  ·  UI/UX Track

| Grant | Digital Egypt pioneers Initiative— UI/UX Track |
| --- | --- |
| Project Type | Graduation Project — UI/UX Design |
| Team Size | 6 Members — UI/UX Designers |
| Duration | 5 Months (20 Weeks) |
| Tools | Figma · FigJam · Maze · Miro · Notion · Google Forms |

# 1. Project Proposal

Hayah (حياة) is a mobile application dedicated to blood donation, presented as a Graduation Project under the Rowad Masr El Raqamiya grant — UI/UX Track. A team of 6 designers focuses on delivering a human-centered, seamless user experience that connects blood donors with patients in need.

## 1.1 Project Overview

| Field | Details |
| --- | --- |
| Project Name | Hayah — حياة · Blood Donation Mobile App |
| Work Scope | UI/UX Design only: Research → Wireframes → UI → Prototype → Handoff |
| Target Users | Blood donors · Patients & families · Hospitals & blood banks |
| Tools | Figma · FigJam · Maze · Miro · Notion · Google Forms |
| Duration | 5 Months (20 Weeks) |
| Grant | Rowad Masr El Raqamiya — Graduation Project · UI/UX Track |

## 1.2 Problem Statement

Egypt faces a chronic blood supply shortage with no unified digital platform connecting donors to patients in real time:

- Patients and families rely on social media posts and personal networks to find donors

- No smart matching system based on blood type and geographic proximity

- Donors receive no recognition, motivation, or sustained engagement

- Hospitals and blood banks operate in silos with no digital integration

## 1.3 Proposed Solution (UX Perspective)

- Smart Matching Flow — fast, effortless connection between donor and patient

- Emergency Mode — visually urgent, attention-grabbing broadcast screen

- Rewards System — badges, points, and digital certificates to motivate donors

- Trust System — verified profiles and ratings that build user confidence

- Community Feed — success stories and help requests fostering belonging

## 1.4 Project Goals

| Design Goals | Graduation Project Goals |
| --- | --- |
| Design a seamless experience for two distinct user types | Deliver a complete project for the Rowad Masr grant |
| Build a unified, consistent Design System | Achieve an excellent score from the evaluation panel |
| Achieve Usability Score ≥ 80% in testing | Publish a professional Case Study on Behance |
| Deliver a fully interactive Figma prototype | Build a strong portfolio entry for each team member |

## 1.5 Project Scope

IN SCOPE ✅

- User Research (Surveys, Interviews, Personas, Empathy Maps, Journey Maps)

- Information Architecture & User Flow Diagrams

- Low-fidelity Wireframes (30+ screens)

- High-fidelity UI Design — Design System + all screens

- Interactive Prototype in Figma

- Usability Testing & Iteration Rounds

- Developer Handoff Documentation

- Case Study + Final Presentation Deck

OUT OF SCOPE ❌

- Code development (Frontend / Backend) — outside UI/UX track

- Publishing the app to the App Store or Google Play

- Integration with hospital or EHR systems

# 2. Project Plan — Timeline (5 Months)

The team follows a design-adapted Agile methodology — 5 phases, one phase per month, each month divided into two weekly sprints (Sprint 1: execution, Sprint 2: review & iteration).

## 2.1 Five-Phase Overview

| M | Phase Name | Key Activities | Duration | Deliverable |
| --- | --- | --- | --- | --- |
| M1 | Research & Discovery | Surveys, Interviews, Competitive Analysis, Personas | 4 weeks | Research Report + Personas + User Journey Map |
| M2 | IA & Wireframes | Sitemap, User Flows, Low-fi Wireframes, Feedback | 4 weeks | Full Wireframes (30+ screens) + Flow Diagrams |
| M3 | UI Design | Design System, Component Library, Hi-fi Screens | 4 weeks | Design System + All Hi-fi Screens (Donor & Requester) |
| M4 | Prototype & Testing | Interactive Prototype, Usability Testing, Iterations | 4 weeks | Tested Prototype + Usability Report + Iterations |
| M5 | Handoff & Presentation | Dev Handoff, Case Study, Behance, Final Deck | 4 weeks | Handoff Docs + Case Study + Presentation + Behance |

## 2.2 Gantt Chart — 20 Weeks

Each color represents a phase · Filled cells = active weeks for each activity

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month 1 — Research & Discovery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User Surveys & Interviews |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Competitive Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personas & Empathy Maps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User Journey Mapping |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Month 2 — IA & Wireframes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Information Architecture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User Flow Diagrams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low-fi Wireframes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wireframe Review & Feedback |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Month 3 — UI Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design System / Tokens |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Library |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hi-fi Screens — Donor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hi-fi Screens — Requester |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Month 4 — Prototype & Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interactive Prototype |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Usability Testing (Maze) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Iteration & Refinement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Design Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Month 5 — Handoff & Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Developer Handoff (Figma) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Case Study Writing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Presentation Deck |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Behance Upload & Portfolio |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## 2.3 Milestones & Deliverables

| # | Milestone | Deliverables | Target Date |
| --- | --- | --- | --- |
| M1 | Research Complete | Research Report · 2+ Personas · User Journey Map · Competitive Analysis (5 apps) | End of Week 4 |
| M2 | Wireframes Approved | Sitemap · User Flows · Low-fi Wireframes (30+ screens) · Feedback Documentation | End of Week 8 |
| M3 | UI Design Complete | Design System · Component Library · Hi-fi Screens (Donor + Requester flows) | End of Week 12 |
| M4 | Prototype Tested | Interactive Figma Prototype · Usability Test Report · Final Iteration Round | End of Week 16 |
| M5 | Final Submission | Dev Handoff (Figma) · Case Study · Presentation Deck · Behance Published | End of Week 20 |

# 3. Task Assignment & Roles

The team consists of 6 members from the UI/UX Track of the Rowad Masr El Raqamiya grant. Each member has a defined role and clear responsibilities, with weekly collaborative reviews across all phases.

## 3.1 Team Roles & Responsibilities

| # | Role | Member | Key Responsibilities | Active Months |
| --- | --- | --- | --- | --- |
| 1 | Team Lead / UX Lead | Adel Mohamed | Team & timeline management · User Research · User Flows · Review all deliverables · Liaison with grant supervisors | All Months |
| 2 | UX Researcher | Omer Abdelfattah | Surveys & Interviews · Competitive Analysis · Personas · Empathy Maps · Usability Testing · Test Reports | M1, M4 |
| 3 | UI Designer — Donor Flow | Arwa Ahmed | Hi-fi Screens for donor journey (Home, Profile, Rewards, Map, Donation History) · Component variants · Design review | M2, M3, M4 |
| 4 | UI Designer — Requester Flow | Abdelmasseh Qadis | Hi-fi Screens for patient journey (Request, Tracking, Chat) · Emergency Mode · Notifications · Onboarding | M2, M3, M4 |
| 5 | Design System Lead | Nada Khaled | Design Tokens · Color/Typography/Spacing System · Component Library · Figma documentation · Design consistency | M2, M3, M5 |
| 6 | Prototype & Handoff Lead | Mariam Mohamed | Interactive Prototype · Usability Testing setup on Maze · Developer Handoff · Case Study · Behance Portfolio | M3, M4, M5 |

## 3.2 RACI Matrix

R = Responsible  |  A = Accountable  |  C = Consulted  |  I = Informed

| Task / Activity | TL | UX Res. | UI Don. | UI Req. | DS | Proto. | M |
| --- | --- | --- | --- | --- | --- | --- | --- |
| User Surveys & Interviews | A/R | R | C | C | I | I | M1 |
| Competitive Analysis | A | R | C | C | I | I | M1 |
| Personas & Journey Maps | A | R | C | C | I | C | M1 |
| Information Architecture | A/R | C | C | C | C | I | M2 |
| Low-fi Wireframes | A | C | R | R | C | C | M2 |
| Design System / Tokens | A | I | C | C | R | I | M2–3 |
| Hi-fi Screens — Donor | A | I | R | I | C | C | M3 |
| Hi-fi Screens — Requester | A | I | I | R | C | C | M3 |
| Component Library | A | I | C | C | R | I | M3 |
| Interactive Prototype | A | I | C | C | I | R | M4 |
| Usability Testing | A | R | C | C | I | R | M4 |
| Design Iterations | A | C | R | R | C | C | M4 |
| Developer Handoff | A | I | C | C | R | R | M5 |
| Case Study & Behance | A | C | C | C | C | R | M5 |
| Final Presentation | A/R | C | C | C | C | C | M5 |

# 4. Risk Assessment

The risks identified below are specific to a UI/UX design project within a grant program — a 6-member student team operating on a 5-month timeline.

## 4.1 Risk Register

| # | Risk | Category | Likelihood | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Team schedule conflicts (exams / other commitments) | Management | High | Medium | Advance planning for breaks, flexible task allocation, async work via Figma & Notion | Team Lead |
| R2 | Team member dropout or prolonged absence | HR | Medium | High | Full documentation on Notion, cross-training, cloud-shared files for all assets | Team Lead |
| R3 | Difficulty recruiting participants for Usability Testing | Research | Medium | Medium | Early outreach in M1, use Maze for remote testing, supplement with peer testing | UX Researcher |
| R4 | Disagreement on Design Direction within team | Design | Medium | Medium | Weekly Design Critique sessions, FigJam voting for group decisions, TL final call | TL + DS Lead |
| R5 | Time pressure & scope creep | Management | High | High | Freeze scope after M2, strict Sprint Planning, no new screens without TL approval | Team Lead |
| R6 | Figma file issues (data loss / version conflicts) | Technical | Low | High | Daily backups, use Figma Branches, clear Page organization & naming conventions | DS Lead + Proto |
| R7 | Low-quality research data (bias / small sample) | Research | Medium | Medium | Target 10+ interview participants, use Screener Survey, apply mixed methods | UX Researcher |
| R8 | UI inconsistency across team members | Design | High | Medium | Design System from M2, weekly Design Review, shared Component Library in Figma | DS Lead |
| R9 | Missing grant submission deadlines | Management | Low | High | One-week buffer built into each phase, daily Notion tracker, submit one day early | Team Lead |
| R10 | Difficulty getting timely feedback from supervisors | External | Medium | Medium | Scheduled weekly check-in with supervisor, prepare specific questions in advance | Team Lead |

## 4.2 Risk Matrix

|  | Low Impact | Medium Impact | High Impact |
| --- | --- | --- | --- |
| High Likelihood | — | R4, R8 | R5 |
| Medium Likelihood | — | R3, R7, R10 | R2, R9 |
| Low Likelihood | — | — | R6 |

🔴 Red = Top Priority  |  🟡 Yellow = Monitor  |  🟢 Green = Low Priority

# 5. Key Performance Indicators (KPIs)

KPIs are tailored to a UI/UX Graduation Project — covering three dimensions: Design Quality, Research & Testing, and Project Delivery.

## 5.1 Design Quality KPIs

| KPI | Target | Measurement Method | Due |
| --- | --- | --- | --- |
| Usability Score (SUS Scale) | ≥ 80 / 100 | System Usability Scale survey post-testing | End of M4 |
| Task Completion Rate | ≥ 85% | Usability Testing sessions (Maze / In-person) | End of M4 |
| Error Rate in Prototype | ≤ 10% of tasks | Recording user errors during testing | End of M4 |
| Design Consistency | 100% Component Coverage | Design System Audit in Figma | End of M3 |
| Screen Coverage (flows complete) | 100% of defined screens | Screen count in Figma vs. Scope doc | End of M3 |
| Accessibility (WCAG AA) | ≥ 90% | Figma Accessibility Plugin + manual check | End of M3 |

## 5.2 Research & Testing KPIs

| KPI | Target | Measurement Method | Due |
| --- | --- | --- | --- |
| Survey participants | ≥ 30 respondents | Google Forms Analytics | End of M1 |
| User interviews conducted | ≥ 8 interviews | Research documentation | End of M1 |
| Usability Testing participants | ≥ 5 users | Maze Dashboard / Session notes | End of M4 |
| Iteration rounds after testing | ≥ 2 rounds | Version history in Figma | End of M4 |
| User Personas coverage | ≥ 3 distinct personas | Research documentation review | End of M1 |

## 5.3 Project Delivery KPIs

| KPI | Target | Measurement Method | Due |
| --- | --- | --- | --- |
| Milestone on-time delivery | 100% on schedule | Notion Project Tracker | Each month |
| Deliverables completion rate | 100% complete | Deliverable checklist | End of M5 |
| Developer Handoff quality | All specs documented | Figma Inspect Mode review | End of M5 |
| Grant jury evaluation score | ≥ 85% | Jury Evaluation Sheet | End of M5 |
| Case Study published on Behance | Yes — published | Behance project link | End of M5 |
| Team satisfaction score | ≥ 8 / 10 | Anonymous team survey | End of M5 |

## 5.4 KPI Review Process

Weekly:  Review Task Board on Notion — are tasks on track? Any blockers?

End of each month:  Group Design Review + Deliverables check + report update

End of M4:  Full analysis of Usability Testing results + written Iteration Plan

End of M5:  Final review of all KPIs + closing project report + Lessons Learned

Any KPI more than 20% below target triggers an emergency team meeting within 48 hours to define a corrective action plan.